## Register
ID | Type | Item | Clarification / Data Request | Working Default / Rationale | Domains | Source Documents | Status | ENGIE Response | Date Raised | Date Closed
PH-001 | Blocking | Target market(s) | Which electricity markets, tariff structures, and ancillary-service products are within the initial delivery scope? | Market rules drive eligibility, dispatch logic, settlement, revenue | Strategy, D2, D3, D4 | SYS-STR-FRM-001 v0.9, A.2.2 v1.3, A.2.3 v1.4, A.2.4 v1.0 | Open
PH-002 | Blocking | Behind-the-meter vs. front-of-the-meter scope | Is the initial delivery expected to support both BTM and FTM configurations, or is one the priority? | Determines which value streams and constraints apply | Strategy, D2, D3, D4 | SYS-STR-FRM-001 v0.9, A.2.2 v1.3, A.2.3 v1.4, A.2.4 v1.0 | Open
PH-003 | Blocking | Data availability | What historical data will ENGIE provide — meter data, market prices, ancillary prices, regulation signals, customer bills — and at what resolution and horizon? | Determines what can be modeled; drives ingestion design | D1, D2 | SYS-STR-FRM-001 v0.9, A.2.1 v1.3, A.2.2 v1.3 | Open
PH-004 | Blocking | Project configuration | What is the primary reference configuration: standalone BESS, co-located with renewables, BTM, FTM, AC- or DC-coupled? | Determines which System Context dimensions are relevant and which interfaces are developed first | Strategy, D7 | SYS-STR-FRM-001 v0.9, A.2.7 v0.3 | Open
PH-005 | Blocking | Benchmark data | What established benchmarks will be used to validate the model? Can ENGIE provide reference cases with expected results? | Defines acceptance and validation | Strategy, D1, D4, D6 | SYS-STR-FRM-001 v0.9, A.2.1 v1.3, A.2.4 v1.0, A.2.6 v0.3 | Open
PH-006 | Blocking | Acceptance thresholds | What quantified accuracy, runtime, and usability criteria define acceptance? | Must be concrete before the thin slice is built | All domains | SYS-STR-FRM-001 v0.9, A.2.1 v1.3, A.2.2 v1.3, A.2.4 v1.0 | Open
PH-007 | Defaultable | Commercial perspective | Should results be shown from ENGIE's perspective as owner or operator, from the client's perspective, or both? | Both supported; owner perspective primary | D6 | SYS-STR-FRM-001 v0.9, A.2.6 v0.3 | Open
PH-008 | Defaultable | Co-located configurations | Does the first project require co-located BESS with renewable generation? | Standalone BESS (per PH-004 default) | Strategy | SYS-STR-FRM-001 v0.9 | Open
PH-009 | Defaultable | Presentation of value (strategy level) | Does ENGIE accept the split between tariff-based savings and market-based revenue? | Accepted (see also PH-055) | Strategy, D6 | SYS-STR-FRM-001 v0.9, A.2.6 v0.3 | Open
PH-010 | Defaultable | Reporting conventions (strategy level) | Are there ENGIE templates or branding requirements for outputs? | Both PDF and Excel; no branding (see also PH-047) | Strategy, D7 | SYS-STR-FRM-001 v0.9, A.2.7 v0.3 | Open
PH-012 | Defaultable | Users and handover | Who are the users and roles, how many, and who will maintain the tool after week 12? | Both business development and technical maintainers | D7 | SYS-STR-FRM-001 v0.9, A.2.7 v0.3 | Open
PH-015 | Defaultable | Battery data | Are vendor degradation curves or warranty terms available for the reference technologies? | Vendor data if available; otherwise literature | D1, D5 | SYS-STR-FRM-001 v0.9, A.2.1 v1.3, A.2.5 v0.4 | Open
PH-016 | Defaultable | SOC bounds and warranty | Are SOC bounds driven by warranty terms, operating policy, or both? | Warranty-driven initially; policy-configurable | D1, D5 | SYS-STR-FRM-001 v0.9, A.2.1 v1.3, A.2.5 v0.4 | Open
PH-017 | Defaultable | SOC window behavior under degradation | Proportional narrowing or preserved kWh reserves? | Proportional narrowing | D1, D5 | SYS-STR-FRM-001 v0.9, A.2.1 v1.3, A.2.5 v0.4 | Open
PH-018 | Defaultable | Multi-cohort aggregation after augmentation | How should SOH be aggregated when multiple cohorts coexist? | Capacity-weighted SOH | D5 | SYS-STR-FRM-001 v0.9, A.2.1 v1.3, A.2.5 v0.4 | Open
PH-019 | Defaultable | Export and net metering | How is exported energy compensated? | Net metering if applicable; otherwise no compensation | D2 | SYS-STR-FRM-001 v0.9, A.2.2 v1.3 | Open
PH-020 | Defaultable | Minimum bill and fixed charges | Are there minimum-bill provisions or fixed charges? | Represented if applicable | D2 | SYS-STR-FRM-001 v0.9 | Open
PH-021 | Defaultable | Power factor penalties / kVAR charges | Do the customer tariffs in scope include power factor penalties or kVAR charges? | Represented if applicable | D2, D3, D4 | SYS-STR-FRM-001 v0.9, A.2.2 v1.3, A.2.3 v1.4, A.2.4 v1.0 | Open
PH-022 | Defaultable | Coincident-peak charges | Where tariffs include coincident-peak charges (e.g. ERCOT 4CP, PJM 5CP), does ENGIE have a peak-prediction approach? | Peak hours assumed known, with configurable hit-rate factor | D2 | SYS-STR-FRM-001 v0.9, A.2.2 v1.3 | Open
PH-023 | Defaultable | Tariff structure detail | How are ratchets, coincident-peak, and billing periods defined? | Represented per tariff rules | D2 | SYS-STR-FRM-001 v0.9 | Open
PH-024 | Defaultable | Tariff escalation | How should tariff escalation be projected? Should the tool also evaluate tariff switching? | Configurable escalation; tariff switching as optional extension | D2, D6 | SYS-STR-FRM-001 v0.9, A.2.2 v1.3 | Open
PH-025 | Defaultable | Load projection growth | What load growth assumptions should apply? Are site changes expected? | ENGIE-provided if available; otherwise statistical baseline | D2 | SYS-STR-FRM-001 v0.9, A.2.2 v1.3 | Open
PH-026 | Defaultable | BESS sizing vs. evaluation | Is the model intended for sizing or evaluation? | Evaluation of a predefined configuration | D4 | SYS-STR-FRM-001 v0.9, A.2.4 v1.0 | Open
PH-027 | Defaultable | Primary model purpose / use case | Project development support or other? | Evaluation (project development support) | D4 | SYS-STR-FRM-001 v0.9, A.2.4 v1.0 | Open
PH-028 | Defaultable | Model output granularity | What level of detail is expected? | All levels (interval schedules, daily/monthly metrics, annual KPIs) | D4 | SYS-STR-FRM-001 v0.9, A.2.4 v1.0 | Open
PH-029 | Defaultable | Active vs. reactive priority | When the inverter's apparent-power limit binds, is there a priority rule? | Project / grid-code dependent | D4 | A.2.4 v1.0 | Open
PH-030 | Defaultable | Dispatch validation benchmark | What benchmark should be used for dispatch validation? | Internal consistency checks | D4 | A.2.4 v1.0 | Open
PH-031 | Defaultable | Revenue attribution under simultaneous services | How should revenue be attributed when services overlap? | Rule-based attribution | D4 | A.2.4 v1.0 | Open
PH-032 | Defaultable | Financial objective inside dispatch | Should degradation cost enter the dispatch objective? | Depends on dispatch methodology (see PH-034) | D5 | A.2.5 v0.4 | Open
PH-033 | Defaultable | Perfect foresight vs. forecast-based dispatch | Which dispatch mode should be the default? | Perfect foresight; realization factor applied in Financial Engineering | Strategy, D2, D3, D4 | SYS-STR-FRM-001 v0.9, A.2.2 v1.3, A.2.3 v1.4, A.2.4 v1.0 | Open
PH-034 | Defaultable | Dispatch methodology | Rule-based heuristic, LP, MILP, or hybrid? | LP | Strategy, D3, D4 | SYS-STR-FRM-001 v0.9, A.2.3 v1.4, A.2.4 v1.0 | Open
PH-035 | Defaultable | Realization factor | What magnitude should apply to market-based revenues? Is it configurable per scenario? | Configurable per scenario; default range to be agreed | Strategy, D6 | SYS-STR-FRM-001 v0.9, A.2.6 v0.3 | Open
PH-036 | Defaultable | Degradation feedback time scale | Frequency of SOH update during operational simulation? | Annual SOH update with representative-period simulation | Strategy, D1, D4, D5 | SYS-STR-FRM-001 v0.9, A.2.1 v1.3, A.2.4 v1.0, A.2.5 v0.4 | Open
PH-037 | Defaultable | Degradation model calibration | How should the model be calibrated if vendor data is unavailable? | Literature-based; validated against benchmarks | D5 | SYS-STR-FRM-001 v0.9 | Open
PH-038 | Defaultable | Degradation feedback time scale (confirmatory) | Confirmation of annual SOH update with representative-period aggregation. | Confirms PH-036 | D5 | A.2.5 v0.4 | Open
PH-039 | Defaultable | Financial objective inside dispatch (confirmatory) | Confirmation of PH-032. | Confirms PH-032 | D5 | A.2.5 v0.4 | Open
PH-040 | Defaultable | Representative-period scheme and ratchets | Monthly representative periods respecting the billing period; where ratchets apply, all 12 months simulated. | Monthly representative periods; 12 months if ratchets apply | Strategy, D4 | SYS-STR-FRM-001 v0.9, A.2.4 v1.0 | Open
PH-041 | Defaultable | Voltage regulation coupling | Should the P² + Q² ≤ S² coupling be linearized, or represented as a fixed envelope? | Fixed envelope — no linearization initially | Strategy, D3, D4 | SYS-STR-FRM-001 v0.9, A.2.3 v1.4, A.2.4 v1.0 | Open
PH-042 | Defaultable | Financing structure | What debt parameters (gearing, interest rate, tenor) should be used for equity IRR? | Default debt parameters provided; configurable by the user | Strategy, D6 | SYS-STR-FRM-001 v0.9, A.2.6 v0.3 | Open
PH-043 | Defaultable | Tax, incentives, and conventions | Should the model include tax, depreciation, and incentives such as the ITC? What currency? Nominal or real? | Pre-tax initially; ITC / depreciation flagged as extension. Nominal cash flows. | Strategy, D5, D6 | SYS-STR-FRM-001 v0.9, A.2.5 v0.4, A.2.6 v0.3 | Open
PH-044 | Defaultable | Augmentation policy | Scheduled, SOH-threshold-triggered, or both? | SOH-threshold-triggered | Strategy, D5 | SYS-STR-FRM-001 v0.9, A.2.5 v0.4 | Open
PH-045 | Defaultable | Replacement policy | Does replacement reset capacity to BOL? | Reset to BOL | Strategy, D5 | SYS-STR-FRM-001 v0.9, A.2.5 v0.4 | Open
PH-046 | Defaultable | Databricks environment | Please confirm workspace ownership, access provisioning, Databricks Apps availability, Unity Catalog usage, and compute policies. | ENGIE-owned workspace; consultant granted developer access | Strategy, D7 | SYS-STR-FRM-001 v0.9, A.2.7 v0.3 | Open
PH-047 | Defaultable | Reporting requirements | Are there ENGIE templates or branding requirements for PDF and Excel exports? | Both PDF and Excel; no branding | Strategy, D6, D7 | SYS-STR-FRM-001 v0.9, A.2.6 v0.3, A.2.7 v0.3 | Open
PH-048 | Defaultable | Audit / lineage / traceability scope | Are execution logs, data lineage, and audit outputs required deliverables, or optional engineering practices? | Basic execution logs + data lineage | Strategy, D7 | SYS-STR-FRM-001 v0.9, A.2.7 v0.3 | Open
PH-049 | Defaultable | Grid constraints | What are the interconnection limits and export constraints at the site? | Represented if provided | Strategy, D2 | SYS-STR-FRM-001 v0.9, A.2.2 v1.3 | Open
PH-050 | Defaultable | Load forecasting method | What method should be used for load projection over the contract term? | ENGIE-provided if available; otherwise statistical baseline | Strategy, D2 | SYS-STR-FRM-001 v0.9, A.2.2 v1.3 | Open
PH-051 | Defaultable | Load forecasting home | Does load forecasting belong to Domain 2 conceptually, with implementation via Domain 7? | Yes — Domain 2 owns it conceptually | Strategy, D2 | SYS-STR-FRM-001 v0.9, A.2.2 v1.3 | Open
PH-052 | Defaultable | Scenario granularity | How many core scenarios should be delivered initially? | 3–5 core scenarios initially, expandable | Strategy, D2 | SYS-STR-FRM-001 v0.9, A.2.2 v1.3 | Open
PH-053 | Defaultable | Market adapter scope | How many market adapters should be delivered at handover? | One adapter at delivery; architecture supports more | Strategy, D2 | SYS-STR-FRM-001 v0.9, A.2.2 v1.3 | Open
PH-054 | Defaultable | Time resolution | What time resolution should the model use — 15-minute, hourly, or a mix? | 15-minute when input data permits; hourly otherwise | Strategy, D2, D4 | SYS-STR-FRM-001 v0.9, A.2.2 v1.3, A.2.4 v1.0 | Open
PH-055 | Defaultable | Presentation of value (BTM mapping convention) | Does ENGIE accept the mapping convention proposed in `A.2.3` §15.2 for attributing behind-the-meter savings to value streams? | Accepted | Strategy, D3, D6 | SYS-STR-FRM-001 v0.9, A.2.3 v1.4, A.2.6 v0.3 | Open
PH-011 | Reserved | (reserved) | Reserved ID — not assigned. Kept for numbering stability. | — | — | — | —
PH-013 | Reserved | (reserved) | Reserved ID — not assigned. Kept for numbering stability. | — | — | — | —
PH-014 | Reserved | (reserved) | Reserved ID — not assigned. Kept for numbering stability. | — | — | — | —

## Summary
Register Summary
Type | Total | Open | Answered / Closed
Blocking | 6 | 6 | 0
Defaultable | 46 | 46 | 0
Reserved | 3 | 0 | 0
Total | 55 | 52 | 0
Note: 'Blocking' = must be resolved in weeks 1-2. 'Defaultable' = proceeds under the working default if not confirmed. 'Reserved' = ID kept for numbering stability.

## Cross-Reference
Cross-Reference
Table 1 — Strategy items (B/D) -> Register ID
Strategy item | Register ID | Topic | Primary Domain | Notes
B1 | PH-001 | Target market(s) | Strategy, D2
B2 | PH-002 | BTM vs. FTM scope | Strategy, D2
B3 | PH-003 | Data availability | D1, D2
B4 | PH-005 | Benchmark data | D6, D7
B5 | PH-006 | Acceptance thresholds | Strategy, all
B6 | PH-004 | Project configuration | Strategy, D5
D1 | PH-034 | Dispatch methodology | Strategy, D3, D4
D2 | PH-033 | Perfect foresight vs. forecast-based dispatch | Strategy, D2, D3, D4
D3 | PH-036 | Degradation feedback time scale | Strategy, D1, D4, D5
D4 | PH-041 | Voltage regulation coupling | Strategy, D3, D4
D5 | PH-050 | Load forecasting method | Strategy, D2
D6 | PH-051 | Load forecasting home | Strategy, D2
D7 | PH-052 | Scenario granularity | Strategy, D2
D8 | PH-042 | Financing structure | Strategy, D6
D9 | PH-043 | Degradation model fidelity / tax treatment | Strategy, D5, D6
D10 | PH-047 | Reporting requirements | Strategy, D6, D7
D11 | PH-053 | Market adapter scope | Strategy, D2
D12 | PH-048 | Audit / lineage / traceability scope | Strategy, D7
D13 | PH-054 | Time resolution | Strategy, D2, D4
D14 | PH-055 | Presentation of value (BTM mapping convention) | Strategy, D3, D6
D15 | PH-046 | Databricks environment | Strategy, D7
D16 | PH-026 | BESS sizing vs. evaluation | D4
D17 | PH-027 | Primary model purpose | D4
D18 | PH-028 | Model output granularity | D4
D19 | PH-040 | Representative-period scheme and ratchets | Strategy, D4
D20 | PH-004 | Project configuration | Strategy, D5

## Legend
Legend
Source of truth | PH1-REG-001.md in the repo. This workbook is a transcription for tracking; if they differ, the markdown prevails and this file is regenerated.
Version | Excel companion v1.3, transcribes PH1-REG-001.md v1.1.
Type: Blocking | Strategy B1-B6 (PH-001 to PH-006). Must be resolved in weeks 1-2.
Type: Defaultable | Proceeds under the working default if not confirmed by end of week 2.
Type: Reserved | ID reserved to keep the Register numbering stable. Not assigned. PH-011, PH-013, PH-014.
Status | Open / Answered / Deferred / Closed / Superseded.
Editable columns | Status, ENGIE Response, Date Raised, Date Closed (yellow).
Example response | PH-019 -> Status: Closed ¦ ENGIE Response: 'Export allowed up to 500 kW; compensated at avoided-cost rate per utility schedule X' ¦ Date Closed: 2026-10-07